## Sheet1
Risk Assessment
Risk ID | Type | Description | Risk Likelihood | Risk Impact | Risk Level | How to Reduce Risk
1 | Internet Connection failing | If my internet connection fails I will no longer be able to connect to my online tools espeacially GitHub since I will no longer be able to use version control if I mess up my code. | Possible | Significant | Medium | Making sure I'm always in close proximity to my Wi fi box so that it is less likely for my internet to disconnect.
2 | Laptop running out of battery | if my battery runs out then any unsaved changes would be lost | Unlikely | Moderate | Low | Regularly checking my laptop so it has enough battery and charging it when it starts to get low.
3 | Adding faulty code | Adding code which causes other areas of the project which were functiong to no longer be able to function | Likely | Significant | High | Regularly commit any changes so I can go back if any of my code no longer functions.
4 | Accidently deleting code | I might delete a branch that has some new code which I have not pushed up to the dev branch which would result in me loosing code. | Possible | Moderate | Medium | Not deleting my branches until the end of the project so id I did not pull any in I can pull the code in later on and readjust as needed.
5 | Forgetting MySQL password | If I forget my password I would be unable to reconnect to my SQL Database | Unlikely | Minor | Low | Making sure my psasword is simple and easy to remeber, plus writing it down if I do forget
6 | Laptop Updates while coding | When an update is due sometimes my laptop might start restart and start an update without requesting it so I could loose the code I was working on | Very Unlikely | Moderate | Low | Regularly saving and commiting changes so I limit the amount of work I could potentially loose
Impact
[9 empty] | Negligible | Minor | Moderate | Significant | Severe
[7 empty] | Likelihood | Very Likely | Low | Medium | High | High | High
[8 empty] | Likely | Low | Medium | Medium | High | High
[8 empty] | Possible | Low | Low | Medium | Medium | High
[8 empty] | Unlikely | Low | Low | Low | Medium | Medium
[8 empty] | Ver Unlikely | Low | Low | Low | Medium | Medium